## Raw Metrics
Comparative Metrics: Waterfall vs Agile
Metric | Waterfall | Agile | Difference
Total development hours | 29.5 | 52.5 | +23.0
Hours: Planning/Documentation | 10 | 7 | -3.0
Hours: Coding | 14.5 | 42.5 | +28.0
Hours: Testing | 0 | 3 | +3.0
Hours: Rework (CRs) | 5 | 8 | +3.0
Total defects found | 0 | 7 | +7
High severity defects | 0 | 1 | +1
Medium severity defects | 0 | 4 | +4
Low severity defects | 0 | 2 | +2
Total defect fix effort (hrs) | 0 | 3.1 | +3.1
CR-001 rework hours | 2 | 2.5 | +0.5
CR-002 rework hours | 0.5 | 1.5 | +1.0
CR-003 rework hours | 2.5 | 4 | +1.5
Total CR rework hours | 5 | 8 | +3.0
Features delivered | 10 | 10 | 0
Delivery rate (%) | 100 | 100 | 0

## Time Breakdown
Development Hours by Phase
Phase | Waterfall (hrs) | Agile (hrs)
Planning/Documentation | 10 | 7
Coding | 14.5 | 42.5
Testing | 0 | 3
Rework | 5 | 8
Total | 29.5 | 60.5

## Defect Comparison
Defect Detection & Fix Effort
Metric | Waterfall | Agile
Total defects found | 0 | 7
High severity | 0 | 1
Medium severity | 0 | 4
Low severity | 0 | 2
Total fix effort (hrs) | 0 | 3.1
Avg fix time per defect (hrs) | 0 | 0.44

## Rework Comparison
Rework Effort per Change Request
Change Request | Waterfall (hrs) | Agile (hrs) | Difference
CR-001: Categories | 2 | 2.5 | +0.5
CR-002: Status Counts | 0.5 | 1.5 | +1.0
CR-003: Comments | 2.5 | 4 | +1.5
Total | 5 | 8 | +3.0

## Agile Burndown
Agile Sprint Burndown
Day | Sprint 1 Planned | Sprint 1 Actual | Sprint 2 Planned | Sprint 2 Actual | Sprint 3 Planned | Sprint 3 Actual
1 | 9 | 9 | 10 | 10 | 8 | 8
2 | 8.1 | 9 | 9 | 10 | 7.2 | 7
3 | 7.2 | 7 | 8 | 8 | 6.4 | 6
4 | 6.3 | 6 | 7 | 7 | 5.6 | 5
5 | 5.4 | 4 | 6 | 5 | 4.8 | 4
6 | 4.5 | 4 | 5 | 5 | 4 | 3
7 | 3.6 | 3 | 4 | 3 | 3.2 | 2
8 | 2.7 | 2 | 3 | 2 | 2.4 | 1
9 | 1.8 | 1 | 2 | 1 | 1.6 | 0.5
10 | 0 | 0 | 0 | 0 | 0 | 0

## Summary Dashboard
Methodology Comparison Summary
Key Metrics
| Waterfall | Agile
Total Hours | 29.5 | 52.5
Defects Found | 0 | 7
Defect Fix Hours | 0 | 3.1
CR Rework Hours | 5 | 8
Features Delivered | 10 | 10
Delivery Rate | 100% | 100%
Key Findings
✓ Agile superior in change management (8 hrs rework vs 5 hrs, but zero schedule impact)
✓ Agile superior in early defect detection (7 defects found and fixed vs 0 in testing phase)
✓ Waterfall superior in upfront planning (10 hrs documentation provided clarity)
✓ Both methodologies achieved 100% feature delivery
✓ Agile more flexible for evolving requirements; Waterfall more predictable for stable requirements